## Sheet1
Reduced production pre-lockdown
Shut down and remobilisation time to implement new SOP's
Reduced production as per supplier data
Pre Covid-19 programme
Months
Piling
Substructure
Cores and frame
Façade
Fit out
Handover/ churn rate
Hoist Apts and final integration
| Covid months - Mar-Dec 2020 | Normal production - Jan 2021 onards
Covid-19 impacted programme
Months
Piling
Substructure
Cores and frame
Façade
Fit out
Handover/ churn rate
Hoist Apts and final integration
Covid impact is 17.07 % increase in overall tower duration assuming there is no second peak and no restrictions from January 2021
COVID-19 impact on a typical 50 storey tower at façade/ fit out interface stage